# Virtual Care Roll-out Project Plan

# Residential Aged Care

| Customer | [Aged Care Provider] |
| --- | --- |
| Home / Facility | [RACH name] |
| Care model | [Nurse-supported virtual care ¦ GP rounds ¦ Urgent reviews ¦ Allied health ¦ Mixed] |
| Version / Date | [v1.0, DD MMM YYYY] |
| Audience | Facility leadership, clinical leaders, IT, privacy, external providers, Visionflex |

Contents

Purpose and scope	2

Success criteria	3

Governance and roles	3

Readiness assessment	3

Phase 1 use cases	4

Workflow design and sign-off	5

Technical deployment and validation	6

Privacy, consent, and information handling	7

Change management and communications	7

Training and competency	7

Go-live and hypercare	8

BAU operations and continuous improvement	8

Sign-off record	9

Useful references (optional)	9

References and useful resources	9

# Purpose and scope

This plan guides the deployment of Visionflex Virtual Care technology in a residential aged care home (RACH). It focuses on making Phase 1 use cases safe, repeatable, and easy to run in day-to-day operations.

This plan provides implementation guidance only. It does not replace clinical judgement, professional standards, or local organisational policy.

## In scope

Agree Phase 1 workflows for selected use cases, including escalation and failover.

Deploy and validate the technical solution (connectivity, access, peripherals, updates).

Train staff and external providers, and confirm basic competency.

Implement privacy and consent processes in routine practice.

Go-live and hypercare support, then transition to business as usual (BAU) operations.

## Out of scope unless added

Commissioning a new clinical service or workforce model.

Internet procurement or network redesign beyond local troubleshooting and coverage improvements.

Changes to the resident clinical system or formal EHR integration work (unless agreed).

Clinical policy development outside the virtual care workflows in this plan.

# Success criteria

The home can run each Phase 1 use case end-to-end using the agreed workflow and escalation pathway, with Clinical Lead sign-off.

Key roles complete training and a short competency check appropriate to their role.

Consent, privacy, and information handling steps are implemented and documented.

A 30 and 90-day review cadence is established with actions to improve adoption and outcomes.

# Governance and roles

Virtual care sits within the organisation’s clinical governance framework. Clinical leaders own the minimum safe workflow and escalation pathways. Executive leadership owns resourcing, risk oversight, and adoption.

| Role | Name | Organisation | Responsibility summary |
| --- | --- | --- | --- |
| Executive Sponsor | [Name] | Customer | Accountable for resourcing, risk oversight, decision escalation |
| Project Lead | [Name] | Customer | Day-to-day coordination, timeline, RAID log, stakeholder comms |
| Clinical Lead (DON/CCM) | [Name] | Customer | Workflow safety, escalation pathways, clinical sign-off |
| Facility Manager | [Name] | Customer | Operational readiness, staffing, space, storage, local escalation |
| IT Lead | [Name] | Customer | Network, device access, security, patching, local IT escalation |
| Privacy Officer (or delegate) | [Name] | Customer | Consent and information handling, privacy risks |
| GP Liaison / Provider Liaison | [Name] | Customer | Engage GPs and allied health, schedule test calls |
| Site Champions (min 2) | [Names] | Customer | On-shift support, peer coaching, issue capture |
| Visionflex Implementation Lead | [Name] | Visionflex | Vendor delivery, enablement, issue triage |

## Meeting cadence

Weekly implementation huddle (30 mins): Project Lead, Clinical Lead, IT Lead, Visionflex

Go-live readiness checkpoint (45 mins): end of Deploy and Train phase

Hypercare check-ins (15 mins): daily for first week if high volume, otherwise twice weekly

30-day review (30 mins): adoption, issues, workflow optimisation

90-day review (45 mins): outcomes, BAU embed, expansion use cases

# Readiness assessment

Readiness is assessed across key domains. Record status as Red, Amber, or Green, with actions and owners.

| Domain | What ready looks like | Owner | Status (R/A/G) | Notes / actions |
| --- | --- | --- | --- | --- |
| Clinical workflow | Phase 1 workflows agreed, escalation and failover defined | Clinical Lead |  |  |
| People and change | Champions nominated, training time allocated | Project Lead |  |  |
| Technical | Network validated, access and accounts set, devices paired | IT Lead |  |  |
| Privacy and consent | Consent and information handling steps documented | Privacy Officer |  |  |
| External providers | GPs and key providers invited, test calls booked | GP Liaison |  |  |
| Operations | Storage/charging location, cleaning process, booking process in place | Facility Manager |  |  |

# Phase 1 use cases

Select up to three Phase 1 use cases. Keep them simple and repeatable.

| Use case | Description | Why it matters | Constraints / notes |
| --- | --- | --- | --- |
| UC1 | [Example: Nurse-supported urgent GP review] |  |  |
| UC2 | [Example: Wound / skin review with external clinician] |  |  |
| UC3 | [Example: Allied health consult or case conference] |  |  |

Examples that often work well in RACHs include GP rounds with onsite nursing support, wound and skin reviews, medication review support, allied health follow-ups, and multidisciplinary case conferences.

# Workflow design and sign-off

Design each Phase 1 workflow so staff can deliver safe, consistent care, with clear responsibilities for clinical appropriateness, consent, documentation, escalation, and failover.

## Use case workflow sheet

Complete one sheet per Phase 1 use case.

| Field | UC1 | UC2 | UC3 |
| --- | --- | --- | --- |
| Use case name |  |  |  |
| Intended outcomes |  |  |  |
| Resident cohort and setting |  |  |  |
| Trigger and booking |  |  |  |
| Participants and roles |  |  |  |
| Clinical appropriateness rules |  |  |  |
| Consent process |  |  |  |
| Pre-call checks |  |  |  |
| In-consult steps |  |  |  |
| Documentation requirements |  |  |  |
| Escalation pathway |  |  |  |
| Technology failover |  |  |  |
| Post-consult follow-up |  |  |  |
| Quality checks (30/90 day) |  |  |  |

## Escalation and deterioration recognition

Define red flags that trigger escalation for each use case.

Define who can escalate (RNs, NPs, senior staff) and where escalation goes during business hours and after hours.

Ensure the escalation pathway is rehearsed and easy to follow under pressure.

Ensure documentation and handover expectations are clear.

## Documentation and communicating for safety

Define the single source of truth for documentation (usually the resident clinical record).

Define how information is provided to external clinicians before the consult (summary, meds list, recent obs).

Avoid splitting clinical information across informal channels. If images or device outputs are captured, specify where they are stored and who can access them.

Confirm medication orders and follow-up actions using the home’s usual processes.

## External provider onboarding

Invite external providers early and confirm preferred contact details.

Book a short test call before the first resident consult.

Confirm the booking and referral pathway, including any clinical information required in advance.

Confirm expected response times for urgent reviews and after-hours coverage.

# Technical deployment and validation

Objective: ensure the solution works reliably in real world conditions such as variable Wi-Fi, shared networks, and mobile coverage.

## Technical checklist

Confirm where the cart or kit will be stored, charged, and kept secure.

Validate Wi-Fi coverage in key locations (nurses station, resident rooms, treatment rooms).

Confirm a backup connectivity option (4G/5G hotspot or SIM-enabled device) where feasible.

Confirm user accounts, permissions, and any required multi-factor authentication.

Pair and test all peripherals required for Phase 1 use cases.

Confirm software update approach and who applies updates (including ProEX updates where relevant).

Run a test call in each intended location and document outcomes.

## Asset control

Maintain an asset register for devices and peripherals to reduce delays during go-live and troubleshooting.

| Asset | Serial / ID | Location | Custodian | Notes |
| --- | --- | --- | --- | --- |
| Cart / Mobile kit |  |  |  |  |
| Tablet / PC |  |  |  |  |
| Camera (GEIS/PTZ) |  |  |  |  |
| Stethoscope |  |  |  |  |
| ECG |  |  |  |  |
| Other peripherals |  |  |  |  |

# Privacy, consent, and information handling

Confirm consent at the start of every session and record it in the resident record.

Confirm who is present on both sides of the call (family, interpreter, trainees).

Use a private space where possible. Use signage if using a shared room.

Do not record sessions unless approved under local policy and consent is obtained.

Handle images and files as health information. Store and share only via approved systems and processes.

# Change management and communications

Nominate champions across shifts and roles.

Set clear expectations for Phase 1 use cases and when virtual care is appropriate.

Publish a simple quick reference near the equipment (how to start, who to call, failover steps).

Engage external providers early and confirm their willingness to participate.

Use a short issues log to capture friction points and fix them quickly.

# Training and competency

Training should be role-based and practical. Focus on running a session end-to-end, including consent, documentation, and escalation.

| Role group | Training focus | Minimum competency check |
| --- | --- | --- |
| RNs / ENs | Setup, starting session, peripherals, consent, escalation, documentation | Run a mock consult end-to-end |
| Care staff | Resident preparation, privacy, assisting during consult | Support a resident through a mock consult |
| Admin / coordinators | Booking, invitations, pre-read pack, follow-up tasks | Schedule and send a test invite correctly |
| External clinicians | Joining calls, communication, expectations, documentation handover | Complete a short test call |
| Champions | Troubleshooting, coaching, issue logging | Troubleshoot common issues in simulation |

Record attendance and completion. Provide refresher training for new staff and for low-use periods.

# Go-live and hypercare

## Go-live readiness checklist

Phase 1 workflows signed off by Clinical Lead

Technical checklist completed and test calls passed

Champions rostered for go-live week

Quick reference guides printed and placed near equipment

External providers onboarded and test calls completed

Support escalation pathway confirmed

## Hypercare plan

Daily check-in for week 1 to capture issues and resolve quickly

Twice weekly check-in for weeks 2 to 4 (or as required)

Log issues in a single issues register and assign owners and due dates

Escalate any patient safety incidents via the home’s usual incident management process

# BAU operations and continuous improvement

Embed SOPs into the home’s quality system and review at 90 days, then annually.

Maintain equipment cleaning, storage, and charging routines.

Review usage monthly (number of sessions, common use cases, failure rates, provider participation).

Run a 30-day and 90-day improvement review with actions.

Confirm a pathway for onboarding new external providers and new staff.

# Sign-off record

Do not proceed to go-live until the sign-offs below are completed.

| Sign-off | Name | Signature | Date |
| --- | --- | --- | --- |
| Clinical Lead (workflow safety) |  |  |  |
| IT Lead (technical readiness) |  |  |  |
| Facility Manager (operations readiness) |  |  |  |
| Project Lead (training and comms) |  |  |  |

# Useful references (optional)

AHPRA virtual care guidance: https://www.ahpra.gov.au/Resources/Information-for-practitioners-who-provide-virtual-care.aspx

OAIC health service provider privacy guidance: https://www.oaic.gov.au/privacy/health-service-providers

# References and useful resources

These links are provided for convenience. Customers should apply their own governance, policies and jurisdictional requirements.

R1. AHPRA – Information for practitioners who provide virtual care: https://www.ahpra.gov.au/Resources/Information-for-practitioners-who-provide-virtual-care.aspx

R2. Medical Board of Australia – Telehealth consultations with patients: https://www.medicalboard.gov.au/Codes-Guidelines-Policies/Telehealth-consultations-with-patients.aspx

R3. RACGP – Principles for conducting telephone and video consultations (consent, introductions): https://www.racgp.org.au/running-a-practice/technology/clinical-technology/telehealth/guide-to-providing-telephone-and-video-consultatio/principles-for-conducting-telehealth-consultations

R4. OAIC – Guide to health privacy: https://www.oaic.gov.au/privacy/privacy-guidance-for-organisations-and-government-agencies/health-service-providers/guide-to-health-privacy

R5. Australian Digital Health Agency – Using Online Conferencing Technologies Securely (PDF): https://www.digitalhealth.gov.au/sites/default/files/2020-11/Online_conferencing_technologies-Connected_secure_consultations.pdf

R6. NSW Agency for Clinical Innovation – Virtual care in practice: Implementation: https://aci.health.nsw.gov.au/virtual-care-in-practice/implementation

R7. NSW Agency for Clinical Innovation – Monitoring, evaluation and research: https://aci.health.nsw.gov.au/virtual-care-in-practice/implementation/monitoring-and-evaluation

R8. Australian Commission on Safety and Quality in Health Care – Safety and quality in virtual care: https://www.safetyandquality.gov.au/our-work/e-health-safety/safety-and-quality-virtual-care

R9. ACSQHC – Recognising and Responding to Acute Deterioration Standard: https://www.safetyandquality.gov.au/standards/nsqhs-standards/recognising-and-responding-acute-deterioration-standard

R10. NSW Clinical Excellence Commission – Embedding virtual care in safety and quality frameworks (PDF): https://www.cec.health.nsw.gov.au/__data/assets/pdf_file/0010/805906/Embedding-virtual-care-in-safety-and-quality-frameworks.pdf

R11. Victorian Department of Health – Virtual Care Operational Framework core elements: https://www.health.vic.gov.au/virtual-care-operational-framework/virtual-care-operating-framework

R12. MBS Online - Factsheet Privacy checklist for telehealth services https://www.mbsonline.gov.au/internet/mbsonline/publishing.nsf/Content/F47F4FC1848FAEC2CA25855D008395C9/$File/Factsheet-privacy-checklist-for-telehealth-services-20200804.pdf