RAID Log

Risks, Assumptions, Issues and Dependencies

Site: [Site name]  |  Project Lead: [Name]  |  Last updated: [DD MMM YYYY]

Record risks, assumptions, issues, and dependencies from the start of the project. Review at each project meeting. Close items when resolved and note the outcome. Escalate items that need a decision.

Type key: Risk = something that might happen  |  Assumption = something you are relying on  |  Issue = something that has happened  |  Dependency = something you need from someone else

Priority: High = blocks go-live  |  Medium = needs resolution before BAU  |  Low = monitor

Status: Open  |  In progress  |  Closed  |  Escalated

The first four rows are examples. Delete them and replace with your own entries.

| ID | Type | Description | Owner | Raised | Priority | Due date | Status | Decision / action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 001 | Risk | Wi-Fi coverage in consult room may be insufficient for reliable video | [IT Lead] | [Date] | High | [Date] | Open | IT to run speed test this week |
| 002 | Assumption | GP practice will allocate one session per week for virtual rounds | [Project Lead] | [Date] | Medium | [Date] | Open | Confirm with practice manager |
| 003 | Issue | Staff roster does not include time for training before go-live | [Ops Manager] | [Date] | High | [Date] | Open | Escalate to Exec Sponsor |
| 004 | Dependency | Consent form must be approved by legal before go-live | [Privacy Officer] | [Date] | High | [Date] | Open | Legal review submitted [Date] |
| 005 |  |  |  |  |  |  |  |  |
| 006 |  |  |  |  |  |  |  |  |
| 007 |  |  |  |  |  |  |  |  |
| 008 |  |  |  |  |  |  |  |  |
| 009 |  |  |  |  |  |  |  |  |
| 010 |  |  |  |  |  |  |  |  |
| 011 |  |  |  |  |  |  |  |  |
| 012 |  |  |  |  |  |  |  |  |
| 013 |  |  |  |  |  |  |  |  |
| 014 |  |  |  |  |  |  |  |  |

This is general guidance, not legal, clinical or financial advice. Always work within your scope of practice and your organisation's policies.